## Backlog
Release | Epic ID | Epic | Feature | Story ID | Story | Acceptance criteria | Role | Estimate (person-days) | Target week | Priority | Depends on | Status | As built (spec · note)
R1 | E1 | Platform Foundation | Infrastructure as Code | S1 | Terraform baseline: repo structure, S3+DynamoDB state, dev/prod env skeletons, networking for Aurora | terraform apply creates empty env in a fresh account | DevOps | 2 | 1 | Must |  | Delivered — P1 | Spec 001 — Terraform, two env roots, S3 + DynamoDB state
R1 | E1 | Platform Foundation | CI pipeline | S2 | GitHub Actions CI: ruff, mypy, pytest+moto, Angular build, terraform validate/plan on PR | All checks gate merges to main | DevOps | 2 | 1 | Must | S1 | Delivered — P1 | Spec 001 — CI grew to 16 required checks
R1 | E1 | Platform Foundation | CD pipeline | S3 | CD with GitHub OIDC roles: auto-deploy dev on merge, gated prod deploy, Alembic migration step | Merge to main reaches dev unattended; prod needs approval | DevOps | 2 | 2 | Must | S2 | Delivered — P1 | Spec 001 — OIDC deploys; auto-deploy is opt-in (DEV_AUTO_DEPLOY), prod unused by decision
R1 | E1 | Platform Foundation | Database | S4 | Aurora Serverless v2 (PostgreSQL) + Alembic baseline schema (tenants, accounts, resources, rules, findings, owners, scans, audit) | Migrations run in pipeline; ERD in repo | BE1 | 2 | 1 | Must | S1 | Delivered — P1 | Spec 001 — Aurora Serverless v2, Alembic (17 migrations)
R1 | E1 | Platform Foundation | Identity | S5 | Cognito user pool, admin/operator/viewer groups, hosted UI, JWT authorizer on API Gateway | Login works end-to-end; role claims in JWT | DevOps | 2 | 2 | Must | S1 | Delivered — P1 | Spec 001 — Cognito, three groups, Lambda authorizer
R1 | E1 | Platform Foundation | API skeleton | S6 | FastAPI + Mangum on Lambda behind HTTP API; Powertools logging/tracing/metrics; health + error envelope | GET /health 200 via CloudFront path; structured logs in CloudWatch | BE1 | 2 | 1 | Must | S1 | Delivered — P1 | Spec 001 — FastAPI + Mangum, Powertools logging
R1 | E1 | Platform Foundation | Observability | S7 | CloudWatch dashboard + alarms (API 5xx, scan failures, DLQ depth) with email alerts | Forced failure pages the team | DevOps | 1.5 | 3 | Should | S3 | Delivered — P2 | Spec 001 — observability module, off by default
R1 | E2 | Account Onboarding & Access | Scanner role | S8 | Two auth modes (roles only): same-account local IAM role for the launch account + CloudFormation CloudPulseScannerRole template (ExternalId) for future cross-account. No access-key auth. | Same-account scan works with zero AssumeRole; cross-account template deploys in <5 min and fails without ExternalId | BE2 | 2 | 1 | Must |  | Delivered — P1 | Spec 002 — same-account and cross-account modes; same-account grants fixed live (T063)
R1 | E2 | Account Onboarding & Access | Registration | S9 | Account registration API: add account (mode, role ARN, scan-region list, default us-east-1), verify via dry-run credential check + minimal describe | Bad role/ExternalId/region rejected with a clear error; regions editable later | BE2 | 1.5 | 1 | Must | S6,S8 | Delivered — P1 | Spec 002 — registration API with ExternalId; failure reason added (T062)
R1 | E2 | Account Onboarding & Access | Admin UI | S10 | Accounts admin page: list/add/verify accounts, scan status per account | Operator onboards an account without touching AWS console (except stack deploy) | FE | 1.5 | 2 | Must | S9 | Delivered — P1 | Spec 002 — accounts page
R1 | E3 | Resource Discovery Engine | Resource model | S11 | Normalized resource model (Pydantic) + provider connector interface (AWS first, Azure-shaped) | Connector contract documented; AWS connector implements it | BE1 | 1.5 | 1 | Must |  | Delivered — P1 | Spec 002 — normalized model + Connector protocol
R1 | E3 | Resource Discovery Engine | Sweep | S12 | Tagging API sweep Lambda: paginated GetResources per region, ARN parsing to service/type | All tagged resources of a test account land normalized | BE2 | 1.5 | 1 | Must | S11 | Delivered — P1 | Spec 002 — Tagging API + Cloud Control sweep
R1 | E3 | Resource Discovery Engine | Enrichers | S13 | Enrichers: EC2 (state, type, launch), EBS (attachment), EIP (association) incl. untagged discovery via describes | Untagged EC2/EBS/EIP appear in inventory | BE2 | 1.5 | 2 | Must | S12 | Delivered — P1 | Spec 002 — EC2, EBS, EIP enrichers
R1 | E3 | Resource Discovery Engine | Enrichers | S14 | Enrichers: S3 (region, creation), RDS (engine, class), Lambda (runtime, last modified) | Fields visible in resource detail | BE2 | 1.5 | 2 | Must | S12 | Delivered — P1 | Spec 002 — S3, RDS, Lambda enrichers
R1 | E3 | Resource Discovery Engine | Orchestration | S15 | Step Functions scan workflow: Map fan-out per account x region x service-group (global services once per account), retries/backoff, concurrency caps; EventBridge daily schedule + on-demand API | Daily scan + UI-triggered scan complete across all registered regions | BE1 | 2.5 | 2 | Must | S12 | Delivered — P1 | Spec 002 — Step Functions, one unit per account × region
R1 | E3 | Resource Discovery Engine | Persistence | S16 | S3 raw snapshot writer + Postgres upsert with scan diffing (first_seen/last_seen/deleted_at; open/close findings hooks) | Deleting a resource in AWS closes it in inventory next scan | BE1 | 2.5 | 2 | Must | S15 | Delivered — P1 | Spec 002 — S3 snapshots + Postgres upsert with diffing
R1 | E3 | Resource Discovery Engine | History | S17 | Scan history recording + API (trigger, duration, counts, status) | History page data matches CloudWatch reality | BE2 | 1 | 3 | Should | S16 | Delivered — P2 | Spec 002/004 — scan history API and page
R1 | E4 | Tag Compliance & Findings | Rules | S18 | Rules-as-data: tag_rules table (case-insensitive keys, required set, allowed values) + admin CRUD API, seeded with the 4 mandatory tags | Rule change applies on next scan without deploy | BE1 | 1.5 | 2 | Must | S4 | Delivered — P1 | Spec 003 — rules as data, five seeded
R1 | E4 | Tag Compliance & Findings | SDA registry | S18a | SDA registry: register SDA (name, owner email, team, project_id/project_name tag values) via API + admin UI; resources attach to SDA at load time; unmatched -> 'No SDA' bucket | Tagged resource shows its SDA; compliance score groups by SDA | BE2 | 1.5 | 2 | Must | S16 | Delivered — P1 | Spec 003 — SDA registry
R1 | E4 | Tag Compliance & Findings | SDA registry UI | S18b | SDA admin page: CRUD + tag-value mapping editor + 'No SDA' triage list | Registering an SDA reclassifies matching resources on next scan | FE | 1 | 3 | Must | S18a | Delivered — P2 | Spec 003/004 — SDA page and “No SDA” triage
R1 | E4 | Tag Compliance & Findings | Validation | S19 | Validation worker: evaluate rules on parent resources, open/close/dedupe findings (missing, invalid, non-standard format) | Finding auto-closes when tag fixed and re-scan runs | BE1 | 2.5 | 2 | Must | S16,S18 | Delivered — P1 | Spec 003 — validation worker, findings lifecycle
R1 | E4 | Tag Compliance & Findings | Scoring | S20 | Compliance score per account/project + API (compliant parents / total parents) | Score matches hand-count on test account | BE2 | 1 | 3 | Must | S19 | Delivered — P1 | Spec 003 — compliance score per account and SDA
R1 | E5 | Ownership Attribution | CloudTrail | S21 | Ownership worker: 90-day LookupEvents for creator on Create*/Run* events; human principal detection (IAM user / SSO) | Creator found for console-created test resources | BE2 | 2 | 2 | Must | S16 | Delivered — P1 | Spec 003 — CloudTrail creator attribution; sweeps fixed live (T046)
R1 | E5 | Ownership Attribution | Fallback | S22 | Frequent-modifier fallback (>=3 human write events) + confidence level + evidence stored; unattributed queue | IaC-created resource falls through to modifier or queue | BE2 | 1.5 | 3 | Must | S21 | Delivered — P2 | Spec 003 — fallback chain
R1 | E5 | Ownership Attribution | Email resolution | S23a | Owner email resolution chain: owner tag if email -> configurable pattern on CloudTrail user_id ({user_id}@domain) -> manual override table; bounce flagging | Pattern change is config only; bounced address flags the owner record | BE2 | 1 | 3 | Must | S21 | Delivered — P2 | Spec 003 — owner email resolution chain + overrides
R2 | E5 | Ownership Attribution | Manual | S23 | Manual owner assignment API + UI on resource detail; owner propagates to notifications | Assigned owner receives the next notification | FE | 1 | 4 | Should | S22 | Out of scope | Per-resource manual assignment not built; identity overrides cover email resolution
R1 | E6 | Notification Engine | Email | S24 | SES domain/identity setup + templated emails (finding summary, deep link, owner name) | Email lands in inbox with working link | DevOps | 1.5 | 2 | Must | S19 | Delivered — P1 | Spec 005 — SES templated email (needs a verified sender to send)
R1 | E6 | Notification Engine | Cadence | S25 | Cadence engine: day 0/2/4 sends per finding, stop on close/acknowledge, mark escalated after 4th interval (manual handling in R1) | Timeline verified with clock-forwarded tests | BE1 | 2 | 3 | Must | S24 | Delivered — P1 | Spec 005 — day 0/2/4 cadence + day-4 escalation flag
R2 | E6 | Notification Engine | Bell | S26 | In-app notifications API: per-user feed, unread count, mark-read | Bell badge updates after scan opens findings | BE2 | 1 | 4 | Should | S19 | Out of scope | In-app notifications cut
R1 | E7 | Governance Dashboard (Angular) | Scaffold | S27 | Angular 18 scaffold: Material theme, layout shell, routing, Cognito PKCE auth + JWT interceptor, role guards | Login/logout works; viewer cannot see admin pages | FE | 2 | 1 | Must | S5 | Delivered — P1 | Spec 004 — Angular 18 shell, Cognito PKCE
R1 | E7 | Governance Dashboard (Angular) | Overview | S28 | Compliance overview: score cards, findings by type/severity charts, per-account table | Numbers match API; loads <2s on 5k resources | FE | 2 | 2 | Must | S20,S27 | Delivered — P1 | Spec 004 — compliance overview (+ AI digest card, spec 006)
R1 | E7 | Governance Dashboard (Angular) | Inventory | S29 | Inventory: server-side paged/filtered table (account, service, region, tag status), resource detail panel with tags/owner/findings | Filter by 'missing owner tag' returns correct set | FE | 3 | 2 | Must | S27 | Delivered — P1 | Spec 004 — inventory explorer, server-side paging
R1 | E7 | Governance Dashboard (Angular) | Findings | S30 | Findings page: list, filter, acknowledge, view notification timeline | Acknowledge stops further emails | FE | 2 | 3 | Must | S29 | Delivered — P1 | Spec 004 — findings workbench (+ suggestions, budget overruns)
R1 | E7 | Governance Dashboard (Angular) | History | S31 | Scan history page (last run, duration, deltas) + on-demand scan button | Button triggers scan; status updates live | FE | 1 | 3 | Should | S17 | Delivered — P2 | Spec 004 — scan operations page
R2 | E7 | Governance Dashboard (Angular) | Bell UI | S32 | Notification bell + feed panel | Unread count correct across sessions | FE | 1 | 4 | Should | S26 | Out of scope | Notification bell cut
R1 | E7 | Governance Dashboard (Angular) | Hardening | S33 | E2E smoke tests (Playwright), empty/error states, deploy polish | CI runs e2e against dev after deploy | FE | 1.5 | 3 | Should | S30 | Delivered — P2 | Spec 004 — Playwright e2e, now run in CI
R2 | E8 | Remediation Engine | Policy | S34 | Policy evaluation: map finding class -> eligible action, auto vs approval-required rules-as-data | Dry-run report lists intended actions per account | BE1 | 3 | 4 | Must |  | Out of scope | Remediation engine out of scope — no write role exists
R2 | E8 | Remediation Engine | Approvals | S35 | Approval workflow: queue, approve/reject API + UI, admin-only, batch approve | Non-admin cannot approve; audit row per decision | FE | 3 | 5 | Must | S34 | Out of scope | Remediation engine out of scope
R2 | E8 | Remediation Engine | Actions | S36 | Remediation actions via CloudPulseRemediatorRole: apply missing tags, correct invalid values (EC2, S3, RDS, Lambda, EBS) | Tags applied in spoke; before/after in audit log | BE2 | 3 | 5 | Must | S34 | Out of scope | Remediation engine out of scope
R2 | E8 | Remediation Engine | Safety | S37 | Dry-run default, per-account opt-in, rollback data (previous tag values), failure retry + DLQ | Kill-switch disables all remediation in <1 min | BE1 | 2 | 6 | Must | S36 | Out of scope | Remediation engine out of scope
R2 | E8 | Remediation Engine | Escalation | S38 | Escalation automation: unresolved after 4th interval -> escalate to project owner + report entry | Escalation email cites full notification history | BE2 | 2 | 6 | Should | S25 | Partly delivered | Day-4 escalation flag built (spec 005); no escalation email
R2 | E9 | Cost Governance | Spend | S39 | Cost Explorer integration: daily spend by project tag/account/service into Postgres (24h granularity) | Spend matches CE console +/-1% | BE1 | 3 | 4 | Must |  | Delivered — P1 | Spec 005 — Cost Explorer daily spend
R2 | E9 | Cost Governance | Budgets | S40 | Auto-create AWS Budgets per project (80%/100% actual+forecast alerts) from project registry | New project gets budget within a day | BE2 | 2.5 | 5 | Must | S39 | Delivered differently | Spec 005 — budgets per SDA inside CloudPulse, not the AWS Budgets service
R2 | E9 | Cost Governance | Overruns | S41 | Overrun detection -> budget findings into the standard findings/notification pipeline | Overrun triggers owner email like a tag finding | BE2 | 2 | 6 | Must | S40 | Delivered — P2 | Spec 005 — overrun → finding in the same workbench
R2 | E9 | Cost Governance | Cost UI | S42 | Cost dashboard: spend by project/SDA/env, trend charts, budget vs actual, drill-down | Drill from org total to single resource spend | FE | 4 | 6 | Must | S39 | Delivered — P1 | Spec 005 — cost dashboard
R2 | E10 | GenAI Insights (Bedrock) | Digest | S43 | Bedrock Converse integration + nightly insight digest job (top findings, cost deltas, trends) -> dashboard card | Digest cites real ARNs/numbers only (validated against DB) | BE1 | 3 | 7 | Must | S39 | Delivered — P1 | Spec 006 — daily digest on Bedrock AgentCore + Nova 2 Lite, grounded; proven live (T144)
R2 | E10 | GenAI Insights (Bedrock) | Suggester | S44 | Remediation suggester: per finding class, action + blast-radius note, shown in approval UI | Suggestions render in approval screen; humans decide | BE2 | 2.5 | 7 | Should | S34 | Delivered differently | Spec 006 — one suggestion per finding (not per class), grounded; proven live
R2 | E10 | GenAI Insights (Bedrock) | Weekly email | S45 | Weekly digest email to admins (SES) from stored insights | Unsubscribes honored; content matches dashboard | BE2 | 1.5 | 8 | Could | S43 | Out of scope | Weekly digest email not built
R2 | E10 | GenAI Insights (Bedrock) | Guardrails | S46 | Prompt suite + eval harness (golden outputs), cost caps, Haiku/Sonnet routing, Bedrock budget alarm | Regression eval runs in CI; monthly Bedrock cost alarm | BE1 | 2 | 8 | Should | S43 | Partly delivered | Spec 006 — eval suite (16 cases) + per-run token cap; single model, no routing
R2 | E11 | Unused Resources & IAM Hygiene | Enrichers | S47 | Enrichers: EKS, DynamoDB, ELB, IAM (roles/users/keys inventory) | New types visible in inventory with detail | BE2 | 3 | 7 | Must | S12 | Delivered — P2 | Spec 002 — EKS, DynamoDB, ELBv2, IAM role enrichers; grants fixed live (T064)
R2 | E11 | Unused Resources & IAM Hygiene | Unused v1 | S48 | Unused detection: idle EC2 (CPU<5% 14d), unattached EBS, orphaned EIP, idle RDS -> findings with monthly savings estimate | Savings estimate within 20% of CE numbers | BE1 | 4 | 8 | Must | S39,S47 | Out of scope | Superseded by utilization (S54) and rightsizing (S52)
R2 | E16 | R2 Hardening | Hardening | S49 | Load test (50 accounts simulated), security review of remediation path, docs refresh | Scan of 50 accounts <30 min; pen-test checklist clean | DevOps | 4 | 8 | Should |  | Out of scope | Load test not run; remediation path does not exist
R3 | E12 | Predictive Intelligence | Metrics | S50 | CloudWatch metrics collection (CPU/mem/network/storage) for EC2/RDS into metrics store (Timestream or Postgres partitioned) | 14d of metrics for all discovered instances | BE2 | 4 | 9 | Must |  | Delivered — P2 | Spec 006 — CloudWatch metrics collector
R3 | E12 | Predictive Intelligence | Forecast | S51 | Spend + capacity forecasting (per project) with trend models; accuracy backtesting | Backtest MAPE < 15% on 3 test projects | BE1 | 5 | 10 | Must | S50 | Delivered — P2 | Spec 006 — least-squares forecasts with backtest
R3 | E12 | Predictive Intelligence | Rightsizing | S52 | Rightsizing recommendations: Compute Optimizer + usage analysis (m5.2xlarge -> m5.xlarge class moves), savings math | Each rec shows evidence + monthly delta | BE1 | 4 | 11 | Must | S50 | Delivered differently | Spec 006 — own low-and-steady CPU analysis, not Compute Optimizer
R3 | E12 | Predictive Intelligence | Narratives | S53 | Bedrock forecast narratives on cost/forecast pages | Narrative numbers match charts exactly | BE2 | 2 | 12 | Could | S51 | Descoped | Spec 006 User Story 7 descoped — narrator built, not displayed
R3 | E13 | Sandbox Utilization | Calc | S54 | Utilization % (used vs provisioned) per account and project | Formula documented; matches manual calc | BE2 | 3 | 11 | Must | S50 | Delivered — P2 | Spec 005 — utilization (active vs idle)
R3 | E13 | Sandbox Utilization | UI | S55 | Utilization pages with account -> project -> resource drill-down | Drill-down in <3 clicks | FE | 3 | 12 | Must | S54 | Delivered — P2 | Spec 005 — utilization page
R3 | E11 | Unused Resources & IAM Hygiene | IAM hygiene | S56 | Unused IAM roles/keys: last-used analysis, access patterns, cleanup recommendations (flag only) | Zero false 'unused' on active roles in test org | BE2 | 4 | 12 | Must | S47 | Delivered — P2 | Spec 005 — IAM hygiene, weekly, flag-only
R3 | E14 | NL Q&A Copilot | Tools | S57 | Read-only tool endpoints for LLM (query inventory, findings, spend) with tenant scoping + limits | Tools reject cross-tenant and write attempts | BE1 | 3 | 12 | Must |  | Out of scope | NL Q&A out of scope (agents do use read-only allowlisted API tools)
R3 | E14 | NL Q&A Copilot | Orchestration | S58 | Bedrock tool-use orchestration loop, answer synthesis with ARN citations, conversation state | 10 canned questions answered correctly | BE1 | 4 | 13 | Must | S57 | Out of scope | NL Q&A out of scope
R3 | E14 | NL Q&A Copilot | Chat UI | S59 | Chat panel in dashboard with streamed responses + citation links | Citation click opens resource detail | FE | 3 | 13 | Should | S58 | Out of scope | NL Q&A out of scope
R3 | E15 | SaaS & Multi-Cloud Readiness | Tenancy | S60 | Tenant onboarding flow: signup, per-tenant ExternalId issue/rotation, tenant admin role | Second tenant sees only its own data (tested) | BE1 | 4 | 13 | Must |  | Out of scope | Single tenant; tenant_id everywhere keeps it possible
R3 | E15 | SaaS & Multi-Cloud Readiness | Metering | S61 | Usage metering (accounts, resources, scans per tenant) for future billing | Metering report per tenant per month | BE2 | 3 | 14 | Should | S60 | Out of scope | Not built
R3 | E15 | SaaS & Multi-Cloud Readiness | Azure spike | S62 | Azure connector spike: implement connector interface with Resource Graph + tags for 5 resource types | Azure resources render in same inventory UI | BE2 | 5 | 14 | Should | S11 | Out of scope | Connector protocol ready; Azure not started
R3 | E15 | SaaS & Multi-Cloud Readiness | Reports | S63 | Report generation: compliance + cost PDF/Excel exports, scheduled email delivery | Monthly report auto-emails to admins | FE | 3 | 14 | Should | S42 | Out of scope | Not built

## Summary
CloudPulse AI — Backlog Summary
Capacity vs load per release
Release | Weeks | People | Raw capacity (pd) | Focus capacity (80%) | Planned load (pd) | Load vs RAW | Load vs FOCUS
R1 | 3 | 4
R2 | 5 | 4
R3 | 6 | 4
Note: R1 runs above focus capacity by design — scope is frozen; overflow stories (marked 'Should') are the cut line.
Load by epic
Epic ID | Epic | Release(s) | Stories | Planned load (pd)
E1 | Platform Foundation | R1
E2 | Account Onboarding & Access | R1
E3 | Resource Discovery Engine | R1
E4 | Tag Compliance & Findings | R1
E5 | Ownership Attribution | R1, R2
E6 | Notification Engine | R1, R2
E7 | Governance Dashboard (Angular) | R1, R2
E8 | Remediation Engine | R2
E9 | Cost Governance | R2
E10 | GenAI Insights (Bedrock) | R2
E11 | Unused Resources & IAM Hygiene | R2, R3
E16 | R2 Hardening | R2
E12 | Predictive Intelligence | R3
E13 | Sandbox Utilization | R3
E14 | NL Q&A Copilot | R3
E15 | SaaS & Multi-Cloud Readiness | R3
TOTAL
Load by role (all releases)
Role | Stories | Planned load (pd)
BE1
BE2
FE
DevOps
As built — story outcomes (October 2026)
Status | Stories
Delivered — P1
Delivered — P2
Delivered differently
Partly delivered
Descoped
Out of scope
TOTAL
Built solo, spec-first, as six feature specs (481 tasks) rather than three releases by four people. The capacity and load figures above are the v1.0 plan, kept for comparison.